## Integration Tasks
# | Priority | Page(s) Affected | Integration / Task | What Needs to Be Done | How to Implement | Common Mistakes / Precautions | Status | Developer Notes
CMS & Content
1 | P0 — Critical | All pages | Sanity.io CMS Setup | Set up Sanity Studio with article + project schemas. Migrate 16 WordPress articles. Connect GROQ queries for dynamic content rendering. | 1. Run `npx sanity@latest init` in project root 2. Create schemas in sanity/schemas/ (article.js, project.js) — schemas provided in Technical Spec doc 3. Configure lib/sanity.js with projectId + dataset 4. Set up Sanity webhook → Vercel rebuild on publish 5. Host Studio at /studio route or studio.purushottam.com 6. Migrate articles using Sanity CLI import or manual entry | • Do NOT use data_only=True when reading — it strips formulas • Ensure GROQ query field names match schema field names exactly • Set up preview mode BEFORE going live — draft viewing is essential for content workflow • Sanity free tier = 100K API calls/month — use ISR (revalidate: 3600) to avoid hitting limits • Image fields need asset->url dereferencing in GROQ | Not started | Schemas are in the Technical Spec document (Section 5). Use dataset 'production'. Free tier is sufficient for launch.
2 | P0 — Critical | All pages | WordPress Content Migration | Migrate all 16 existing articles from basavapurushottam.com (WordPress) into Sanity CMS with correct slugs, pillars, tags, and body content. | 1. Export WordPress content via WP REST API or WXR export 2. Parse HTML body into Sanity's Portable Text format 3. Map each article to correct pillar (ai-governance, policy-lab, philosophy, ai-foundations, field-notes) 4. Verify slugs match those used in JSX hub pages 5. Set publishedAt, readTime, tags, featured flag per article | • WordPress HTML → Portable Text conversion loses formatting if not handled carefully — use @sanity/block-tools • Slugs MUST match exactly what's in the hub pages (e.g., 'markov-brain', 'barnum-effect-ai') • Don't forget to set the 'featured' boolean on key articles • OG images need to be re-uploaded to Sanity CDN, not hotlinked from WordPress | Not started | Full article list with slugs in Technical Spec Appendix A (16 articles).
Newsletter & Email
3 | P0 — Critical | All pages (9 files) | Beehiiv Newsletter Integration | Connect the 3 newsletter form variants (general, mind, policy) to Beehiiv API for real email capture. | 1. Create Beehiiv publication 'Signal from the Frontier' 2. Build API route: app/api/subscribe/route.js 3. POST to Beehiiv API: https://api.beehiiv.com/v2/publications/{pub_id}/subscriptions 4. Pass email + tag (variant: general/mind/policy) for segmentation 5. Enable double opt-in in Beehiiv settings 6. Replace placeholder form onSubmit with real API call 7. Handle loading, success, and error states in UI | • Rate limit the subscribe endpoint (5 req/hr per IP) to prevent abuse • Validate email server-side, not just client-side • Beehiiv API key goes in Vercel env vars, NEVER in client-side code • The tag/segment must be passed at subscription time — you can't retroactively segment • Test with a real email before launch — Beehiiv's sandbox doesn't send actual emails | Not started | 3 variants exist in code: general (homepage, about, proving-ground, contact), mind (mind-and-machine, article-detail, late-compiler), policy (policy-lab). Beehiiv free tier = 2,500 subscribers.
4 | P1 — High | N/A (Beehiiv) | Beehiiv Welcome Email Sequence | Set up 3-email automated welcome sequence: Day 0 (welcome + top articles), Day 3 (guided reading path), Day 7 (intro to AI chatbot). | 1. Create automation in Beehiiv dashboard 2. Write 3 emails with links to actual published articles 3. Day 0: Welcome + links to Markov Brain, Ancient Dreams, UPSC Probabilistic Analysis 4. Day 3: Suggest reading path based on subscriber tag 5. Day 7: Introduce 'Ask Purushottam AI' chatbot (when live) 6. Set trigger: on new subscription | • Do NOT activate the sequence before articles are migrated — broken links in welcome emails are terrible • Test the entire sequence on yourself first • Ensure unsubscribe link is working in every email (GDPR compliance) | Not started | This is a content task — no code needed. Can be done in parallel with dev work.
Google Sheets Integration
5 | P1 — High | 05-proving-ground.jsx | Google Sheets → Accountability Board | Create Google Sheet workbook with 3 tabs (Weight, Running, Hiking). Build API route to fetch live data. Render stat tiles, weight trend chart, and activity log. | 1. Create Google Sheet with columns: Date ¦ Weight (kg) ¦ Activity (Running/Walking/Hiking) ¦ Distance (km) ¦ Duration (min) ¦ Notes 2. Create Google Cloud service account + enable Sheets API 3. Share sheet with service account email (read-only) 4. Build Next.js API route: app/api/progress/route.js 5. Use googleapis npm package to fetch data 6. Parse rows, compute: current weight, total change, total distance, streak 7. Cache with ISR (revalidate: 3600) 8. Replace placeholder stat tiles with real computed values 9. Build Chart.js line chart for weight trend 10. Build activity log (last 14 days) with toggle view | • Service account key is a JSON file — store it as a Vercel env var (base64 encode the JSON), NOT in the repo • Google Sheets API has quota: 300 req/min — use ISR caching, don't fetch on every page load • Date parsing: Google Sheets returns dates as serial numbers — use moment or dayjs to parse • The sheet must be shared with the service account email, not made 'public' • Handle empty sheet gracefully — show 'No data yet' instead of crashing | Not started | Dr. Purushottam will update the sheet manually every morning. Placeholder stat tiles and chart container already exist in the JSX.
6 | P1 — High | 09-the-late-compiler.jsx | Google Sheets → Syllabus Board | Create Google Sheet with 5 tabs (one per track: AI Fundamentals, Applied AI, Agentic AI, Machine Learning, Python from Zero). Connect to syllabus section. | 1. Create Google Sheet with 5 tabs 2. Columns per tab: Week # ¦ Lesson Title ¦ Type (Blog/Video/Exercise) ¦ Status (Published/This week/Upcoming) ¦ Link ¦ Description 3. Reuse same service account from task #5 4. Build API route: app/api/syllabus/route.js 5. Fetch all 5 tabs, return as JSON grouped by track 6. Replace hardcoded sample lessons in Syllabus component with live data 7. Color-code status badges: Published=#10B981, This week=#3B82F6, Upcoming=#57534E | • Tab names in the sheet MUST match exactly what the code expects — case-sensitive • If a tab is empty, return an empty array, don't crash • Status values must be exact strings: 'published', 'this-week', 'upcoming' • Add a 'View the full Google Sheet →' link at the bottom — the link is already in the JSX but points to a placeholder URL | Not started | Sample lesson data is already in the JSX as placeholder. Replace with API data once connected. The syllabus section is placed after TrackSelector and before WhoIsThisFor.
Search & AI
7 | P2 — Medium | All pages (nav bar) | Fuse.js Client-Side Search | Replace the prompt() search placeholder in the nav bar with a full-screen search overlay. Index all articles, projects, and lessons. | 1. npm install fuse.js 2. Create SearchOverlay component (React portal or fixed overlay) 3. Build search index at build time from Sanity data (title, excerpt, tags, pillar) 4. On search icon click → open overlay with auto-focused input 5. Fuse.js options: keys=['title','excerpt','tags'], threshold=0.3, includeScore=true 6. Render results grouped by pillar with article cards 7. Keyboard: Escape closes, arrow keys navigate, Enter opens 8. Close on backdrop click | • Don't import fuse.js in the main bundle — use dynamic import: const Fuse = (await import('fuse.js')).default • The search index should be built at build time, not fetched on every keystroke • Debounce the search input (300ms) to avoid performance issues • Ensure the overlay has proper focus trapping for accessibility • Don't forget to handle 'no results' state gracefully | Not started | Search icon (⌕) already exists in nav bar on all 9 pages. Currently triggers prompt(). The search should cover all articles across all hub pages.
8 | P2 — Medium | All pages (floating widget) | Ask Purushottam AI Chatbot (RAG) | Build RAG chatbot: vectorize all published content, store in Pinecone, query via Claude API with retrieved context. | 1. Chunk all articles into ~500 token segments 2. Embed chunks using OpenAI text-embedding-3-small or Voyage AI 3. Store in Pinecone (free tier: 1 index, 100K vectors) 4. Build API route: app/api/chat/route.js 5. On user query: embed query → search Pinecone top 5 → pass to Claude with system prompt 6. System prompt template is in Technical Spec Section 8.3 7. Include source article links in response 8. Rate limit: 10 queries/user/hour (by IP or session) 9. Max response: 500 tokens | • NEVER expose the Anthropic API key to the client — all calls go through your API route • Pinecone free tier has cold start latency (~2-3s) — show a loading spinner • Chunk overlap: use 50-token overlap between chunks to avoid losing context at boundaries • The system prompt must explicitly say 'answer ONLY from context' to prevent hallucination • Don't stream initially — simpler implementation. Add streaming later for UX polish | Not started | Model: claude-sonnet-4-20250514. System prompt in Tech Spec Section 8.3. Chatbot teaser exists on homepage ('Ask Purushottam AI').
Analytics & Performance
9 | P1 — High | All pages | Analytics Setup (Plausible + Vercel) | Set up Plausible Analytics (privacy-friendly) and Vercel Analytics for performance monitoring. Track custom events. | 1. Create Plausible account, add purushottam.com as site 2. Add Plausible script to app/layout.jsx: <script defer data-domain='purushottam.com' src='https://plausible.io/js/script.js'></script> 3. Enable Vercel Analytics in Vercel dashboard (zero config) 4. Enable Vercel Speed Insights 5. Track custom events: newsletter_signup, article_read (with pillar), chatbot_query, cta_click 6. For Plausible custom events: plausible('newsletter_signup', {props: {variant: 'mind'}}) | • Plausible script must have 'defer' attribute — without it, it blocks rendering • Do NOT use Google Analytics — it requires cookie consent banners. Plausible is cookie-free • Custom event names are case-sensitive in Plausible • Vercel Analytics auto-tracks Web Vitals — don't duplicate with manual tracking • Plausible Growth plan ($9/mo) is needed for custom events — free plan doesn't support them | Not started | Estimated cost: $9/mo for Plausible Growth. Vercel Analytics is free on Pro plan.
10 | P1 — High | All pages | SEO & Structured Data | Add per-page metadata, JSON-LD structured data (Person, Article, BreadcrumbList), XML sitemap, robots.txt, Open Graph images. | 1. In app/layout.jsx: set default metadata with Next.js generateMetadata() 2. Per-page metadata in each page.jsx (titles and descriptions in Tech Spec Section 9.1) 3. JSON-LD: Person schema on /about, Article schema on /insights/[slug], Organization site-wide 4. Sitemap: use next-sitemap package or app/sitemap.xml/route.js 5. robots.txt: app/robots.txt/route.js — allow all crawlers 6. OG images: use @vercel/og for auto-generation (1200x630px) 7. Register in Google Search Console, submit sitemap | • Each page MUST have a unique <title> and <meta description> — duplicate titles kill SEO • JSON-LD must be valid — test at schema.org/validator before deploying • Canonical URLs must be set on every page — use metadata.alternates.canonical • Don't forget to set up 301 redirect: basavapurushottam.com → purushottam.com • OG images must be exactly 1200x630px — other sizes get cropped on LinkedIn/Twitter | Not started | Target keywords and per-page titles are in Technical Spec Section 9. Priority keywords: 'AI governance India', 'National Education Policy 2020 architect'.
User Experience
11 | P2 — Medium | 03, 04, 05, 08, 09 | localStorage Reading Progress | Track which articles each visitor has read. Show checkmarks on read articles in hub listings. Show 'Continue reading' banner. | 1. On article page: when scroll depth > 80%, save: localStorage.setItem('read_' + slug, Date.now()) 2. On hub pages: check localStorage for each article slug → show ✓ badge 3. On any page: check if last article was < 80% read → show 'Continue reading' sticky banner 4. Use a custom hook: useReadingProgress(slug) 5. This is client-only — wrap in 'use client' directive | • localStorage is NOT available during SSR — always check typeof window !== 'undefined' • Use try-catch around localStorage calls — Safari private browsing throws on setItem • Don't track reading progress on hub pages — only on /insights/[slug] • The 80% threshold should be based on article body height, not page height (nav/footer inflate it) • Clear stale entries older than 90 days to avoid localStorage bloat | Not started | TODO comments already exist in 03, 04, 05, 09 JSX files marking where this should go.
12 | P2 — Medium | 05-proving-ground.jsx | Comments Integration (Giscus + Disqus + WhatsApp) | Add commenting/feedback section below the Accountability Board. Three channels: Giscus (GitHub), Disqus, and WhatsApp community link. | 1. Giscus: Create GitHub Discussions repo, configure at giscus.app, embed <script> component 2. Disqus: Create Disqus site, embed universal code with data-page-url and data-page-identifier 3. WhatsApp: Replace placeholder https://chat.whatsapp.com/ with actual group invite URL 4. Layout: Tab selector for Giscus ¦ Disqus, WhatsApp link as standalone CTA | • Giscus requires a PUBLIC GitHub repo — don't use a private repo • Disqus adds ~300KB of JS — lazy load it (only when user scrolls to comments section) • WhatsApp group links expire after a set number of uses — use a 'community' link instead of a group invite • Both Giscus and Disqus need the canonical page URL as identifier — hardcode purushottam.com, not localhost | Not started | User wants all three (Giscus, Disqus, and WhatsApp link). Placeholder WhatsApp link already in JSX.
Deployment & Infrastructure
13 | P0 — Critical | All pages | Next.js Project Setup | Create Next.js 14 app with App Router. Port all 9 JSX prototype files into proper Next.js pages. Configure Tailwind, fonts, global styles. | 1. npx create-next-app@latest purushottam-site --app --tailwind 2. Map files to routes: • 01-homepage → app/page.jsx • 02-about → app/about/page.jsx • 03-mind-and-machine → app/mind-and-machine/page.jsx • 04-policy-lab → app/policy-lab/page.jsx • 05-proving-ground → app/proving-ground/page.jsx • 07-contact → app/contact/page.jsx • 08-article-detail → app/insights/[slug]/page.jsx • 09-the-late-compiler → app/the-late-compiler/page.jsx 3. Extract shared components (Nav, Footer, Newsletter, Fade) into components/ directory 4. Set up next/font for Playfair Display + Source Sans 3 5. Configure global layout in app/layout.jsx with Nav + Footer | • Each prototype file duplicates Nav/Footer/Newsletter — extract these into shared components FIRST before porting pages • The inline styles work in prototypes but should be converted to Tailwind classes for maintainability • Mark interactive components with 'use client' — Nav (scroll state), Newsletter (form state), Testimonials (carousel state) • next/font requires importing in layout.jsx and passing className — don't use <link> tags • The article detail page uses [slug] dynamic route — this needs generateStaticParams() for SSG | Not started | 9 JSX prototypes are the source of truth. All inline styles can be kept initially and migrated to Tailwind incrementally. Priority: get pages rendering first, optimize later.
14 | P0 — Critical | All pages | Vercel Deployment + DNS | Deploy to Vercel. Configure custom domain purushottam.com. Set up SSL, redirects, and environment variables. | 1. Connect GitHub repo to Vercel 2. Set Framework Preset: Next.js 3. Set Node.js version: 20.x 4. Set region: Bombay (bom1) for Indian audience 5. Add environment variables (see list below) 6. DNS: A record purushottam.com → 76.76.21.21, CNAME www → cname.vercel-dns.com 7. Set up www → apex redirect (non-www canonical) 8. 301 redirect: basavapurushottam.com → purushottam.com 9. Enable preview deployments for PR previews | • Environment variables with NEXT_PUBLIC_ prefix are exposed to client-side code — NEVER prefix API keys with NEXT_PUBLIC_ • DNS propagation takes 24-48 hours — set up DNS first, deploy second • The 301 redirect from basavapurushottam.com needs to be configured at the old domain's registrar, not Vercel • Vercel Pro plan ($20/mo) is needed for analytics and better limits — free tier has 100GB bandwidth/month • Set up Vercel's preview deployment comments for code review workflow | Not started | Env vars needed: NEXT_PUBLIC_SANITY_PROJECT_ID, NEXT_PUBLIC_SANITY_DATASET, SANITY_API_TOKEN, ANTHROPIC_API_KEY, PINECONE_API_KEY, PINECONE_INDEX, BEEHIIV_API_KEY, BEEHIIV_PUBLICATION_ID, GOOGLE_SHEETS_CREDENTIALS (base64)
15 | P1 — High | All pages | Font Loading | Load Playfair Display (weights 400, 600, 700) and Source Sans 3 (weights 400, 500, 600) via next/font for optimal performance. | 1. In app/layout.jsx: import { Playfair_Display, Source_Sans_3 } from 'next/font/google' 2. Configure with subsets: ['latin'], display: 'swap' 3. Apply via className to <html> or <body> 4. Reference in components via CSS variables or direct className 5. Remove any <link> tags to Google Fonts CDN | • next/font downloads fonts at BUILD time — no external requests at runtime. This is the correct approach, not CDN links • Must specify all needed weights explicitly — next/font doesn't include weights you don't list • display: 'swap' is critical for CLS — without it, text is invisible during font load • Playfair Display italic is a separate import if needed: style: 'italic' | Not started | Currently fonts are referenced as strings in inline styles ('Playfair Display', Georgia, serif). The next/font setup makes them self-hosted and eliminates layout shift.
16 | P1 — High | Homepage, Article Detail | Professional Portrait Photo | Replace the 'BP' initials placeholder circle with Dr. Purushottam's actual professional portrait photo. | 1. Obtain professional portrait photo from Dr. Purushottam 2. Optimize: serve at 340px, 680px, 1024px widths 3. Use next/image component for automatic WebP, responsive sizes, lazy loading 4. Replace the placeholder div (gold gradient circle with 'BP' text) with <Image> component 5. Set alt text: 'Dr. B.V.R.C. Purushottam, IAS' 6. Also update the author card in article detail template | • next/image requires width+height props or fill={true} with parent position:relative • Don't use a massive source image (>2MB) — optimize to ~200KB max before upload • The portrait container is 340x420px with borderRadius 24 — ensure the image respects this • Upload to Sanity CDN for automatic optimization, not to /public folder | Blocked | BLOCKED: Waiting for Dr. Purushottam to provide the photo. This is the single highest-impact visual improvement for the site.
Content & Miscellaneous
17 | P1 — High | All pages | Real Social Media URLs | Replace placeholder Twitter (https://twitter.com) and Facebook (https://facebook.com) with actual profile URLs. | 1. Get actual Twitter/X handle from Dr. Purushottam 2. Get actual Facebook profile URL 3. Update SOCIAL_LINKS array in ALL 9 JSX files 4. Also update FOOTER_COLUMNS Connect section in ALL 9 files 5. Verify all links open correctly in new tab | • Twitter/X URLs changed format — it's now x.com/handle, not twitter.com/handle (both redirect, but use the canonical x.com) • Facebook profile URLs can be either facebook.com/username or facebook.com/profile.php?id=12345 — get the clean vanity URL • Must update in ALL 9 files — the SOCIAL_LINKS array is duplicated in every file (will be deduplicated when extracted into shared components) | Blocked | BLOCKED: Waiting for Dr. Purushottam to provide actual URLs. LinkedIn URL is already correct.
18 | P2 — Medium | All pages | URL Redirects (/projects → /proving-ground) | Set up 301 redirect from /projects to /proving-ground so old links don't break. | In next.config.js: async redirects() { return [{ source: '/projects', destination: '/proving-ground', permanent: true }] } | • Must be 301 (permanent), not 302 (temporary) — 302 doesn't transfer SEO juice • Also redirect /projects/* patterns if any deep links existed • Test the redirect after deployment — Vercel caches redirect configs aggressively | Not started | The /projects page has been deleted and merged into /proving-ground. All internal links already updated to /proving-ground.
19 | P2 — Medium | Global | RSS Feed Generation | Generate /feed.xml with all published articles for RSS readers. | 1. Create app/feed.xml/route.js 2. Fetch all articles from Sanity 3. Generate RSS 2.0 XML with title, description, link, pubDate per item 4. Set Content-Type: application/xml 5. Add <link rel='alternate' type='application/rss+xml'> to layout.jsx <head> | • RSS dates must be RFC 822 format (e.g., 'Mon, 01 Jan 2026 00:00:00 GMT') • CDATA-wrap HTML content in <description> to avoid XML parsing errors • The RSS link in the footer already points to /feed.xml — make sure the route matches | Not started | Footer already has an RSS Feed link pointing to /feed.xml.
20 | P3 — Low | 07-contact.jsx | WhatsApp Community Link | Replace placeholder https://chat.whatsapp.com/ with actual WhatsApp community invite URL. | 1. Dr. Purushottam creates a WhatsApp Community (not just a group) 2. Generate invite link from WhatsApp settings 3. Replace URL in 07-contact.jsx and 05-proving-ground.jsx and 09-the-late-compiler.jsx | • WhatsApp Group links have a join limit — use a Community link instead which doesn't expire • Must update in 3 files: contact, proving-ground, and late-compiler | Blocked | BLOCKED: Waiting for Dr. Purushottam to create the WhatsApp community and share the invite link.

## Environment Variables
Variable | Description | Where Used | How to Get | Secret?
NEXT_PUBLIC_SANITY_PROJECT_ID | Sanity project identifier | lib/sanity.js | Sanity dashboard → Settings → API | No
NEXT_PUBLIC_SANITY_DATASET | Dataset name (production) | lib/sanity.js | Set to 'production' | No
SANITY_API_TOKEN | Read token for server-side queries | API routes | Sanity dashboard → Settings → API → Tokens → Add Token (read) | Yes
ANTHROPIC_API_KEY | Claude API key for chatbot | api/chat/route.js | console.anthropic.com → API Keys | Yes
PINECONE_API_KEY | Pinecone vector DB key | api/chat, api/search | app.pinecone.io → API Keys | Yes
PINECONE_INDEX | Pinecone index name | api/chat, api/search | Create index in Pinecone dashboard | No
BEEHIIV_API_KEY | Newsletter platform key | api/subscribe/route.js | Beehiiv dashboard → Settings → Integrations → API | Yes
BEEHIIV_PUBLICATION_ID | Publication identifier | api/subscribe/route.js | Beehiiv dashboard → Settings → General → Publication ID | Yes
GOOGLE_SHEETS_CREDENTIALS | Service account JSON (base64) | api/progress, api/syllabus | Google Cloud Console → IAM → Service Accounts → Create Key → JSON → base64 encode | Yes
GOOGLE_SHEET_PROGRESS_ID | Accountability board sheet ID | api/progress/route.js | From the Google Sheet URL: docs.google.com/spreadsheets/d/{THIS_ID} | No
GOOGLE_SHEET_SYLLABUS_ID | Syllabus sheet ID | api/syllabus/route.js | From the Google Sheet URL | No
PLAUSIBLE_DOMAIN | Analytics domain | layout.jsx | Set to 'purushottam.com' | No

## File → Route Map
JSX Prototype File | Next.js Route | URL Path | Newsletter Variant | Has ExploreMore? | Gold Accents
00-shared-components.jsx | components/ (extracted) | N/A (shared) | All 3 variants defined here | No | None (demo page)
01-homepage.jsx | app/page.jsx | / | general | No | 'Algorithmic' in hero headline
02-about.jsx | app/about/page.jsx | /about | general | Yes (4 cards) | 'learning', 'shaping' in hero; 'by choice', 'Himalayas', 'conversation'
03-mind-and-machine.jsx | app/mind-and-machine/page.jsx | /mind-and-machine | mind | Yes | 'Machine' in hero headline
04-policy-lab.jsx | app/policy-lab/page.jsx | /policy-lab | policy | Yes | 'Policy' in hero headline
05-proving-ground.jsx | app/proving-ground/page.jsx | /proving-ground | general | Yes (3 cards) | 'Proving' in hero headline
06-projects.jsx | DELETED | DELETED (/projects → 301 to /proving-ground) | N/A | N/A | N/A
07-contact.jsx | app/contact/page.jsx | /contact | general | Yes | 'Connect' in hero headline
08-article-detail.jsx | app/insights/[slug]/page.jsx | /insights/{slug} | mind | Yes | None (dynamic title)
09-the-late-compiler.jsx | app/the-late-compiler/page.jsx | /the-late-compiler | mind | Yes | 'curiosity' in closing note